# AI Job Search Assistant - Task Steps Checklist

Based on Requirements Spec V1.0 | 60 Tasks | 2026-08-02

Critical Path: Phase 0 -> 1 -> 2 -> 3 -> 4 -> 5 -> 6 (mandatory serial); Phase 7/9 can run in parallel after Phase 6; Phase 8 requires Go/No-Go gate.

# Phase 0: Scope Freeze & Engineering Init (8h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T0-01 | Freeze v1 scope in docs/mvp_scope.md: single-user, Streamlit, CSV/JSON, SQLite, Chroma, 1 LLM + 1 Embedding. No real-time collection, login, multi-account, or auto-apply in v1. | 1h |
| T0-02 | Init repo & env: Git repo, venv, requirements.txt, .gitignore, .env.example, README skeleton, basic startup commands. | 2h |
| T0-03 | Create directory structure & interface contracts: models/, sources/, repositories/, services/, prompts/, ui/, tests/. Define minimal interfaces: JobSource, JobRepository, Retriever, LLMService. | 3h |
| T0-04 | Define error, logging & config conventions: categorize data/storage/retrieval/model/user errors; unify log fields, user prompts, config loading. | 2h |

# Phase 1: Data Model & Sample Preparation (30h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T1-01 | Define domain models: JobPosition, Company, JobRequirement, UserProfile, AIAnswer. Specify field types, required/nullable, unknown/parse-failure states. | 4h |
| T1-02 | Prepare anonymized samples: 50-200 CSV/JSON records covering cities, salary, education, experience, missing values, duplicates, anomalies. Write field dictionary. | 5h |
| T1-03 | Implement LocalFileJobSource: unified CSV/JSON reader with encoding handling, column mapping, batch read, source tracking. Output domain models or clear errors. | 4h |
| T1-04 | Implement Pandas cleaning pipeline: normalize whitespace, missing values, salary ranges, experience, education, dates, skill lists, anomalies. Output cleaning report. | 8h |
| T1-05 | Implement dedup & source tracking: deduplicate by job ID, detail URL, or company+title+city; retain source, source_url, published_at, collected_at. | 4h |
| T1-06 | Write data unit tests: cover salary/date parsing, missing values, invalid input, dedup, CSV/JSON consistency, cleaning reports. | 5h |

# Phase 2: Storage & Structured Search (30h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T2-01 | Design SQLite schema & migrations: tables for jobs, companies, job_requirements. Primary keys, unique constraints, foreign keys, common query indexes. Init scripts. | 5h |
| T2-02 | Implement JobRepository: encapsulate insert, update, batch write, query by ID, list query. Define transaction boundaries. No direct SQL from UI. | 5h |
| T2-03 | Implement combined filtering: keyword, city, job type, salary, experience, education, publish date. Define null and range intersection rules. | 7h |
| T2-04 | Implement sorting & pagination: sort by publish date, salary, relevance. page, page_size, max return limit. | 4h |
| T2-05 | Implement job detail service: aggregate job, company, requirements, source fields by job ID. Preserve missing status and collection time. | 4h |
| T2-06 | Write repository & search tests: cover DB creation, duplicate import, city/salary/experience/education filters, multi-condition, pagination, sorting, empty results. | 5h |

# Phase 3: Vector Index & Hybrid Retrieval (30h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T3-01 | Design index text & metadata: combine title, responsibilities, requirements, nice-to-haves, tech stack. Metadata: job ID, city, salary, education, version, content hash. | 4h |
| T3-02 | Integrate Embedding & lock version: choose cost-effective Chinese Embedding. Configure batch, timeout, retry. Record model name, dimensions, version. | 4h |
| T3-03 | Implement Chroma index lifecycle: initial build, incremental update, delete stale records, full rebuild. Use job ID + content hash to avoid duplicate vectors. | 5h |
| T3-04 | Implement structured filter + semantic retrieval: SQLite candidate IDs first, then Chroma similarity within candidates. Return top-k, scores, original jobs. | 7h |
| T3-05 | Build retrieval eval set: design >= 20 queries covering exact conditions, semantic expressions, synonyms, no-results, conflicting conditions. Annotate expected hits. | 5h |
| T3-06 | Tune & log retrieval parameters: compare top-k, min score, index text variants, fusion rules. Record hit rate, failure cases, final config. | 5h |

# Phase 4: Evidence-based RAG Answers (42h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T4-01 | Encapsulate LLMService & config: centralized model, API URL, timeout, temperature, key management, retries, testable model doubles. | 3h |
| T4-02 | Define evidence context schema: serialize retrieval results with evidence IDs, job IDs, fields, source links, collection times, user profile source. | 4h |
| T4-03 | Write & version RAG prompts: require model to distinguish facts/analysis/suggestions, use only given evidence. Define answer structure, missing-info rules, prohibitions. | 5h |
| T4-04 | Implement verifiable citations: map evidence numbers in answers back to job ID/name, fields, source links. Validate citation validity before output. | 4h |
| T4-05 | Implement domain boundary gating: rule-first, model-fallback to judge job-search relevance. Out-of-domain questions return standard refusal without retrieval. | 3h |
| T4-06 | Implement insufficient-info handling: when retrieval empty, evidence contradictory, fields insufficient — list missing info and next steps. | 3h |
| T4-07 | Implement job matching analysis: compare UserProfile vs job requirements item by item. Output match points, gaps, risks, actionable prep suggestions. | 6h |
| T4-08 | Implement recruiter reply draft generation: editable concise replies. Known info used directly; unknown info uses explicit placeholders with user confirmation prompts. | 5h |
| T4-09 | Build RAG safety & regression tests: cover answered/unanswered/contradictory evidence, out-of-domain, citation errors, prompt injection, model timeout. Offline + limited online. | 9h |

# Phase 5: Streamlit Interactive Loop (34h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T5-01 | Build app shell & page state: search, results, detail, Q&A areas. Define session_state keys for page state. | 3h |
| T5-02 | Implement search controls & validation: keyword, city, salary, experience, education, publish date filters. Validate ranges and nulls. | 5h |
| T5-03 | Display result list: job title, company, city, salary, experience, education, update time, match summary, pagination. | 5h |
| T5-04 | Display job detail & sources: responsibilities, requirements, nice-to-haves, company, source, collection time, missing field status. List/detail navigation. | 5h |
| T5-05 | Wire up Q&A, matching & reply suggestions: pass current job, candidates, user profile to RAG. Show answer, citations, missing info prompts. | 6h |
| T5-06 | Complete loading, error & degradation states: loading, empty results, data failure, vector DB failure, model failure, config missing, retry, local fallback. | 4h |
| T5-07 | Solidify end-to-end demo scripts: prepare 3 fixed paths (job search, matching, recruiter reply) with demo data. Record steps and expected results. | 6h |

# Phase 6: Testing, Errors & Local MVP Delivery (26h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T6-01 | Unified error handling & observability: categorize file/DB/vector/model/network exceptions. Log fields, user prompts, correlation IDs, limited retries. | 4h |
| T6-02 | Sensitive info & privacy audit: scan .env, git history, logs, samples, tests, screenshots. Remove real accounts, resumes, chat logs, keys. | 3h |
| T6-03 | Run full automated tests: data, DB, filters, retrieval, domain gating, citation validation, key UI/service integration tests. Record coverage. | 5h |
| T6-04 | MVP acceptance & defect convergence: verify AC-02, AC-04, AC-05 and local-substitute AC-01/AC-03/AC-06. Record evidence, defects, retest results. | 5h |
| T6-05 | Complete README & ops docs: architecture, install, env vars, data import, index build, startup, testing, troubleshooting, costs, known limitations. | 5h |
| T6-06 | Freeze & release v0.1-local-mvp: record code, dependencies, model, Embedding, Prompt, samples, eval set versions. Generate release notes & tag. | 4h |

# Phase 7: History, Redis & UX Enhancement (28h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T7-01 | Save cleanable business history: use SQLite for search filters, viewed jobs, AIAnswer. Define retention, query & delete endpoints. | 6h |
| T7-02 | Add short-term session memory: Redis List/Stream for last 10-20 messages. session_id, TTL (~24h), refresh on each write. | 6h |
| T7-03 | Add job favorites: save favorite status, notes, time. Reference job ID only. Handle job失效 or deletion. | 4h |
| T7-04 | Add reviewable reply templates: save common templates. Allow job field references for drafts. Unknown info uses placeholders. Preview & edit support. | 5h |
| T7-05 | Test isolation, TTL & degradation: verify session_id isolation, message limit, TTL refresh, concurrent writes, Redis-unavailable fallback. | 7h |

# Phase 8: BOSS Data Source Research & Compliant Integration (48-80h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T8-01 | Compliance & feasibility Go/No-Go: review platform ToS, public APIs, robots/rules, display use, data retention, frequency. Document legal/platform risks and allowed boundaries. | 8-16h |
| T8-02 | Verify allowed access methods: prioritize official APIs, user export, low-frequency manual methods. Record success rate and limits with minimal samples. | 6-10h |
| T8-03 | Implement BossJobSource adapter: implement list reading under existing JobSource contract. Record search params, source, collection time, access status. Feature-flag controlled. | 8-12h |
| T8-04 | Implement detail parsing & structure change detection: parse job description, requirements, company, recruiter public fields. Preserve original refs. Flag missing and structural changes. | 8-12h |
| T8-05 | Wire into existing cleaning, storage & index: feed real-time data into Phase 1-3 pipelines (clean, dedup, SQLite, Chroma). Define update and invalidation policies. | 6-8h |
| T8-06 | Add access protection & failure degradation: low-frequency access, timeouts, limited retries, login-failure detection, structure alerts, circuit breaker, local data fallback. | 6-10h |
| T8-07 | Execute real-time data acceptance: re-run AC-01, AC-03, AC-06. Check field completeness, duplication rate, collection time, failure rate, error messages. | 6-12h |

# Phase 9: Deployment & Portfolio Preparation (18h)

| ID | Execution Step & Deliverable | Est. |
| --- | --- | --- |
| T9-01 | Prepare public demo data: create anonymized job samples, user profile samples, fixed demo queries. Label as samples with update time. | 4h |
| T9-02 | Add architecture, evaluation & decision docs: explain structured/vector division of labor, citation design, adapter layer, degradation, test metrics, key trade-offs. | 4h |
| T9-03 | Deploy demo version & verify: choose local or Streamlit-capable env. Configure keys, storage, startup, health check, minimal monitoring. | 6h |
| T9-04 | Document limitations & release checklist: note data freshness, platform rules, model risks, sample scope, costs, non-auto-apply boundary. Pre-demo checklist. | 4h |

Note: Estimates are effective engineering hours (including implementation, self-testing, and necessary docs). Critical path: Phase 0->1->2->3->4->5->6 (serial). Suggested checkpoints: after Phase 0-2 show a reliable job search tool; after Phase 3-4 show evidence-based RAG core; after Phase 5-6 release local MVP.